## Slide 1: Scope of work – Prioritized list
Priority order | Work item | Description | Estimate Range (hrs.) | Assumptions/Comments
1 | Pega Selenium starter kit integration, pilot 2 test cases on Pega 8.4 version | Integrate current framework with Pega-Selenium JARs Ensure framework still supports 6.4 and execute test cases on both versions with same framework confirming backward compatibility | 150 - 180 hrs. | 4UM application on version 8.X should be available in any test environment for this work item
2 | Framework updates, pilot a test scenario on a Java Web portal application | Framework as is ready for working on automation for a Java web portal Additional JARs, minor changes but not limiting to additional utilities needed to update framework Automation 1 test scenario on the application | 60 - 80 hrs. | If application not available, the effort estimated will be offloaded to the work item of test automation scripting of regression cases
3 | Automation code coverage reports | Measure code coverage, bugs & vulnerabilities, duplication blocks Generate reports depicting above mentioned data points | 80 -100 hrs. | SonarQube is available on marketplace of MyEclipse on HMHS and available for use.
4 | Build management | Integrate with build management tool approved within HMHS for code deployment Managing the process of converting raw source code into a distributable package | 60 – 80 hrs. | HMHS team support is needed to integrate automation script with the build management tool
Priority

## Slide 2: Scope of work – Prioritized list (…continued)
Priority order | Work item | Description | Estimate Range (hrs.) | Assumptions/Comments
5 | Excel report for manual testers to read the results report | Generate an excel report having all the log statements along with Request id generated. | 50 – 60 hrs. | 
6 | Regression test cases scripting - HMHS | Approximate count with test case estimates model | 350 – 370 hrs. | Complete ~630 steps ( ~7 test cases)
7 | Scripting support for HMHS developers by Deloitte | Support HMHS developers with working sessions, issues resolutions | 60 – 70 hrs. | 
8 | Regression test cases scripting - Deloitte | Approximate count with test case estimates model | 200 – 230 hrs. | Complete ~360 steps (4 test cases)
Priority
With experience from POC phase:
Approximating that an average test has cases 90 test steps to automate
Each test case would need around 50 person for automation scripting
Test case Estimation model
Capacity Model | Developer | Capacity available
Deloitte | Vijay Mandavilli | 100%
 | Savita Ghavari | 100%
 | Debkumar Das | 100%
HMHS | Keeley Johansen | 100%
 | Sridevi Boddhula | 20%
 | Sandeep Chalsani | 20%
 | Robert Malone | 20%