## Slide 1: Data migration
Client example
<<Client>> S/4HANA journey involves maintaining existing legacy systems for a period of time as SAP S/4HANA Systems are deployed and integration with third party systems is accomplished.
Based on our experience on similar Health care and/or wholesale and distribution projects, <<Client>> must be prepared to address specific challenges around data conversion and migration:
Data consolidation across multi sources can be time consuming effort; an early start is required
Data cleansing is a huge undertaking and requires a considerable amount of time to complete
Multiple transformation rules may be applied across multiple data sources and result in inconsistent data standards; business alignment will be critical
Establishment of a data organization with data stewards and data owners identified to help with the design and decision making is critical
Data is a significant asset in any business, and a successful migration is crucial to the overall success of not only the project but the business as well. Getting stakeholders involved early and often is instrumental to migration success. Deloitte’s approach puts stakeholders at the center of the process by:
Communicating with stakeholders on a regular basis and emphasizing the importance of data cleanup and conversion
As the data cleansing process will start early and will require stakeholder engagement from the beginning, Deloitte will provide stakeholders with reports and tools to identify potential issues and exceptions swiftly and make data validation a more efficient process
Deloitte’s Kinetic Data Migration suite and our pre-built templates will drive the consolidation of multiple sources of data and will help stakeholders save time and efforts. Deloitte will be using programs which are built on SAP Data Services and Information Steward to profile and analyze data quality on an ongoing basis. Kinetic Data Migration also has capability to monitor the data using pre-built Fiori dashboards
Establishing clear data ownership and defining the Data Governance Organization early will:
Accelerate the review of existing data standards
Identify any additional data standards needed to manage data in the to-be solution
Ensure the business team members are leveraged to the right amount of time required for making decisions, as well as reviewing outputs from data profiling and cleansing to finalize outcomes for data migration
Our approach
In the Phase 0/Prepare phase, a project work plan will be developed containing all conversions of master and transactional data activities, dependencies, timing, and sequencing of programs, as well as data ownership.
In the Blueprint/Explore phase, the data clean-up and conversion process will involve detailed analysis of different data types across different data sources. These different sources of data need to be rationalized into a consistent metadata framework to be loaded into SAP. A consistent and repeatable solution will be provided to support the ongoing critical business processes. Collaboratively, Deloitte will facilitate the cleansing process by providing profiling reports and data quality remediation reports using SAP Data Services and Information Steward. These reports will then be reviewed by the business, working with the Deloitte team, to identify and understand the exceptions and make decisions to move forward on cleansing as well as data migration. The cleansing and data quality will be achieved in a steady manner with a Crawl, Walk, Run approach where initial data cleansing targets are set to a lower threshold of all active data and slowly working through the cleansing targets to achieve a 100%. A sample of how the cleansing is achieved is provided below for reference.

## Slide 2: Data migration
Client example
In the Test phase, mock data loads will be executed, and the output of the mock data loads will be fed into multiple integration test cycles and User Acceptance Testing (UAT). Each mock load will result in improved levels of data completeness, accuracy, and quality. Basic master data will be scrutinized early in the project to improve quality and completeness of converted data in each iteration. Working as a team with <<Client>>, test scenarios will be executed along with data validation scripts. Deloitte will fix data migration defects and <<Client>> will provide inputs and approvals to remediate the data cleansing related defects to either automate cleansing or requires manual fixes to the data.
In the Deploy phase, a Dress Rehearsal load will be performed. Results will be provided as an input to the Go/No-Go decision.
In the Run phase, the data will be loaded in production, and data reconciliation reports will be run to verify that all in-scope source data is moved in S/4HANA or SAP MDG targets.
In addition, the data governance organization, as described in the Master Data Management section, will be established early in the implementation process. This will ensure that the new data management processes are used to throughout the data migration process. This approach will help institutionalize new processes prior to Go-live to enable ongoing data quality in the new global S/4HANA system.
SAMPLE
The example of key concepts proposed solution architecture are described in the following table.

## Slide 3: Data migration
Client example
Concept | Description
Extract | Extract the data from Non-SAP and SAP source systems or from excel/flat file exports. There should be minimal logic in extraction programs. The extracted data is placed in staging area, which is a relational database.
Stage | This holds the raw data extracts that will be further used for profiling, cleansing, and harmonization before loading into the S/4HANA environment or the Global Databases.
Data Profiling | Data profiling is performed using Information Steward to assess the data quality, data compliance with target systems, and business impact. It also helps identify cleansing requirements to resolve the data anomalies before migrating the data to the target systems.
Data Cleansing, Enrichment, and Harmonization | Data cleansing includes: Entering missing data in the source system or through construction templates Deactivating records no longer needed in the source system Updating bad address data in source Merging identified duplicate records (master data and transactions) Standardizing name and address data for customers and vendors Cleansing for Customer/Vendor address data can be performed using the SAP address dictionaries, while for the other objects we can define custom cleansing rules and build a cleansing package
Transforming data to Template | Implement the business transformation rules on the cleansed data in the staging environment and Transform it into a common data layout for the migration object (tables and columns). This includes: Field and value mapping Source to S/4HANA value or ID translation Default values Conditional mapping Consolidation of duplicates Merging enriched data from a third party with extracted data
Data Validation | The cleansed and enriched load files are validated for data integrity and accuracy before they are loaded into the system. Validation includes reviewing the load file for matching the legacy records counts, confirming the target data formats, confirming accuracy of data, and ensuring completeness of the load file. The files are signed-off by the project and business owners before they are loaded into the system.
Data Load | The load of transformed data into SAP S/4HANA is managed using: a. IDOCS – directly posted from BODS b. ABAP load programs c. BAPI For historical data, direct table loads are performed into the target systems.
Data Reconciliation | After the load to the target system, data reconciliation is performed between source and target system data sets to confirm that all the data has been loaded completely and correctly.

## Slide 4: Data migration
Client example
Activities, deliverables and <<Client>> considerations
Blueprint/Explore |  | 
Activities | Representative Deliverables/Work products | <<Client>> Considerations
Fit-gap analysis Data quality assessment Sequence Data Objects Set up system connections and validate connectivity Develop data dictionaries for all the data objects in-scope (Mapping, Business/Transformation Rules, Standards, etc.) | Data migration strategy Data conversion and cleansing plan Data quality snapshots and profiling report Data architecture design Functional specifications and mapping sheets Legacy integration plan Legacy systems retirement plans | <<Client>> to validate the proposed solution and consider the cost and complexity reduction opportunities that would impact overall roadmap approach Decide the best transaction system data access approaches when eliminating and/or consolidating current application instances Data from multiple source systems must be rationalized into a consistent metadata framework to be loaded into SAP
Differentiators: Deloitte’s Data Cleansing Accelerators will support business resources to identify the data enrichment scope. Deloitte’s Kinetic Data Migration suite comes with 61 pre-Built functional specifications and mapping sheet templates for master data and transactional data objects. This will provide jump start to define business requirements and will significantly reduce business efforts. |  | 
Prepare |  | 
Activities | Representative Deliverables/Work | <<Client>> Considerations
Identify Data Types Define Data Maturity Model Define draft Data Model Define cleansing scope, rules and effort | Project Plan Workshop schedule Resource identification Data Migration Approach Initial Information Model | Evaluate and assess current data processes Form data profiling and cleansing teams early Approve and validate scope of data Align data experts with good understanding of existing data issues in business processes to quickly prioritize and assess complexity of data migration by object
Differentiators: Deloitte’s Data Strategy Approach and Data Profiling Accelerators will reduce business efforts to identify the data transformation scope. The data profiling rulesets consist of ~300 rulesets which validate the completeness and uniqueness of the legacy data. This provides an early indication of <<Client>> data quality. |  | 

## Slide 5: Data migration
Client example
Activities, deliverables and <<Client>> considerations
Realize – Build |  | 
Activities | Representative Deliverables | <<Client>> Considerations
Define Load templates and cross reference mapping Build ETL programs Technical Unit Testing Functional Unit Testing Identify data object dependencies via data dry runs. Develop initial cutover plan | Technical Specifications and Load templates ETL (Extract, Transform and Load) executables Technical Unit test results Functional Unit test results ETL dashboards and monitoring tools | Involves the identified business owners for the data object to review and validate the data extracted from the different sources. Validate the loaded data in S/4HANA Work with teams for data enrichment timelines and align them with the mock loads Provide enriched data extract for unit testing Provide any backend IT support needed Approve unit test results and cutover plan
Differentiators: Deloitte’s Kinetic Data Migration suite of pre-built data services jobs includes 54 ETL programs to support extraction, transformation, and load via SAP Data services. Additionally, the pool of 61 conversion load programs provides the flexibility of direct loads in S/4HANA for objects which do not require transformation. These prebuilt programs will expedite the build phase and will reduce development efforts by 30%. |  | 
Realize – Test |  | 
Activities | Representative Deliverables | <<Client>> Considerations
Execute mock cutovers Execute data validation scripts Evaluate data completeness, accuracy and quality Data Load optimization Leverage loaded data for integration testing cycles | Mock cutover plan User acceptance sign-off Data migration dashboard Data validation reports and sign off approach Data validation scripts | Assign dedicated resources by business unit to test and approve Aid in resolving defects from unit testing Aid in data validation for each mock Each mock load will result in improved levels of data completeness, accuracy, and quality
Differentiators: Deloitte’s pre-built End-to-End Migration Dashboards provide real time insights and quality reports. Deloitte’s Data validation tools makes the post load validation easier and significantly reduces business efforts. Additionally, the Pre-to-Post Load comparison provides field level visualization of data anomalies. The pool of data validation scripts segregated by industry group reduces business team efforts to build scripts by 60%. |  | 

## Slide 6: Data migration
Client example
Activities, deliverables and <<Client>> considerations
Deploy |  | 
Activities | Representative Deliverables | <<Client>> Considerations
Execute Dress Rehearsal User acceptance Testing Data Validation and sign off from business data owners Prepare for final cutover Manage error handling Go/No-Go analysis and decision | Dress Rehearsal plan Data migration dashboard Data reconciliation reports Data validation and sign off Go/No-Go analysis | Assign resources for user acceptance testing Aid in resolving defects from UAT Prepare systems and business users for dress rehearsals and final cutover Aid in final Go/No-Go decisions
Differentiators: Automation via RPA Bots expedites migration activities to ensure business effort is invested only to review “true” failures. Pre-built tableau dashboards monitor progress and reporting which is critical for Go/No-Go analysis. |  | 
Run |  | 
Activities | Representative Deliverables | <<Client>> Considerations
Execute final cutover Data Validation and sign off from business data owners Provide hyper-care support Transition to managed services team Project closeout activities | Production cutover plan Data migration dashboard Data reconciliation reports Data validation and sign off Hypercare metrics and reports | Data will be loaded in production and data reconciliation reports will be run to verify that all in-scope source data is moved in S/4HANA or SAP MDG targets Assign resources to be trained for hyper-care Aid in transitioning to services team Approve and sign-off on close-out activities

## Slide 7: Data migration
Client example
Our data migration accelerators
Tool | Description | Project Implication
Kinetic data migration toolset for SAP S/4HANA | Our all-encompassing solution brings methodology, business process and industry knowledge, accelerators and templates under one umbrella to accelerate your migration process Deloitte’s end-to-end data migration approach Predefined data quality rules for profiling and automated data cleansing Compliment SAP RDS (Rapid Data Solutions) with a prebuilt SAP Data Services and ABAP programs for SAP S/4HANA Pre-built data conversion execution tracking dashboards Predefined data validation and reconciliation templates Data quality/readiness assessment approach and scorecards | A comprehensive, SAP S/4HANA-centric, reusable set of templates and tools enables <<Client>> to accelerate the conversion work associated with each roll-out and, most importantly, manage risk in this critical area.
Data Quality Framework for SAP | Data Quality Reference Architectures: SAP-specific reference architectures for the leading data quality toolsets. Reference architectures are available for a variety of technology scenarios. SAP Data Quality Risk Matrix: Identifies key risks and data quality considerations by key data domain. Data Profiling Quick Start Scripts and Templates: Custom data profiling scripts to jump-start data profiling. Data Quality Business Rule Library: Library of SAP-specific data quality business rules for key data domains. | One of <<Client>> challenges is harmonizing disparate business processes with varying levels of data standards, leading to varied levels of data quality. This SAP-centric set of tools enables <<Client>> to assess and confirm whether the quality of its data is fit for use.